## BNCA Ledger Extraction Project
# | Requirement Raise Date | Requirement Brief | What we did | Requirement completion Date | Requirement analysis and understanding | Data gathering (Survey/google form creation) | Demo on survey | Validifying the data | Data Cleaning -(For Python Data Frame and PowerBI Dashboard) | Creating wire frame for intended dashboard | Review on wire frames | Data base connectivity testing- | Python Development | Dashboard Development | Peer Review | Correction to the dashbooard | Internal testing of the dashboard | UAT | Deployment |  | Total Duration in Hours | Total Duration
1 | August - September 2023 | Extraction of the first sample ledger copy in PDF format | Extracted the sample pdf using Python |  | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 2 |  |  | 10
2 | August - September 2023 | Extraction of Basic Student info-PRN, Seat No, Mother Name, Student Name. | Extracted the rquired details using Python | 11th September | 1 | 0 | 0 | 1 | 2 |  |  | 0 |  | 0 | 0 | 0 | 1 | 0 |  |  | 5
3 | 18th September 2023 | Functionality for Semester Wise data (10 Semesters), S.G.P.A., C.G.P.A., Result, Credits Semester-wise, and Class student records. | Added functionality for Semester Wise data (10 Semesters), S.G.P.A., C.G.P.A., Result, Credits Semester-wise, and Class | 2023-09-01 | 2 | 0 | 0 | 2 | 4 |  |  | 0 | 4 | 0 | 0 | 0 | 0 | 1 |  |  | 13
4 |  | Received three additional ledgers on 6th October 2023. | Extracted the rquired details of 4 ledgers. | 31st October 2023 | 1 | 0 | 0 | 1 | 4 |  |  | 0 | 4 | 0 | 0 | 0 | 2 | 1 |  |  | 13
5 |  | Exportion of Dataframe into Excel/Google Sheets. | Extracted data stored into Dataframe and exported into Excel/Google Sheets. |  | 0 |  |  | 0 | 0 |  |  | 5 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 6
6 |  | Dashboard to Analyze all students academics. | Implemented search options for PRN, Seat number, Semester Year, and Name Wise. Analyzed and displayed the count of students Passed, Failed, or Failed With A.T.K.T. Developed a feature to display a particular student’s entire result in one table. | [5 empty] | 4 |  |  |  |  | 2 | 1 | 2 | 2 | 2 |  |  | 13
7 | 11th December 2023 | Extraction of Year Pattern and Ledger Year to the existing data. | Extracted the Year and Ledger Pattern using Python and added to the final data frame. | 12th December 2023 | 1 |  |  | 1 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 5
0
8 | 11th December 2023 | Subject and Grades of all students | Worked on Three Ledgers - Extracted below stuff - YearWise_Student_Info_df24, YearWise_Grades_df272, YearWise_SGPA_df272, YearWise_Result_df72 | 28th December 2023 | 2 |  |  |  | 4 | [11 empty] | 6
18th December received New Sample data ledgers/files
Ledgers for extarction are -
[20 empty] | Final Duration | 71

## BNCA Project Work Stuff Report
# | Requirement Raise Date | Requirement Brief | What I did | Current work Issues / Respective work difficulties / Observations / Findings | Current Status | Requirement completion Date
1 | August - September 2023 | Extraction of the first sample ledger copy in PDF format | Extracted the sample pdf using Python
2 | August - September 2023 | Extraction of Basic Student info-PRN, Seat No, Mother Name, Student Name. | Extracted the rquired details using Python |  |  | 11th September
3 | 18th September 2023 | Functionality for Semester Wise data (10 Semesters), S.G.P.A., C.G.P.A., Result, Credits Semester-wise, and Class student records. | Added functionality for Semester Wise data (10 Semesters), S.G.P.A., C.G.P.A., Result, Credits Semester-wise, and Class |  |  | 2023-09-01
4 |  | Received three additional ledgers on 6th October 2023. | Extracted the rquired details of 4 ledgers. |  |  | 31st October 2023
5 |  | Exportion of Dataframe into Excel/Google Sheets. | Extracted data stored into Dataframe and exported into Excel/Google Sheets.
6 |  | Dashboard to Analyze all students academics. | Implemented search options for PRN, Seat number, Semester Year, and Name Wise. Analyzed and displayed the count of students Passed, Failed, or Failed With A.T.K.T. Developed a feature to display a particular student’s entire result in one table.
7 | 11th December 2023 | Extraction of Year Pattern and Ledger Year to the existing data. | Extracted the Year and Ledger Pattern using Python and added to the final data frame. |  |  | 12th December 2023
8 | 11th December 2023 | Subject and Grades of all students | Worked on Three Ledgers - Extracted below stuff - YearWise_Student_Info_df24, YearWise_Grades_df272, YearWise_SGPA_df272, YearWise_Result_df72 |  |  | 28th December 2023
18th -20th December 2024
| 18th December received New Sample data ledgers/files | Ledgers for extarction are - 5 | Extacted First Semester data only. | 1) Ledgers for extarction are - 5 Downloaded however 3 are not getting downloaded as they are .rar files. 2) Diffucult to understand different files with slightly different structure. 3) If we follow line by line spliting on ledger 2019 pattern - April 2020 crd pnts are printed/shifted on next line . So this is creating a problem. 4) Extacted First Semester data only.
21st December 2024
|  |  |  | 1) While extracting Oct-2019 ledgers's First semester data. I observed there are only 16 columns of marks i.e. marks are distributed in 16 columns. In other ledgers marks are distributed in 18 columns. Like Int1, Ext1, Int2, Ext2. What to do? which & how many should we consider for extraction...? 2) "*" is creating a problem to fetch all 8 subjects in dataframe. 3) "----" keeping as it is. 4) "FFF" is not getting into "Tot" column & it got shifted into next column & further values as well. So is there any criteria & what is the logic how to consider any particular chracter occuring into these lines & specifically because of space they are creating a problem. | As of now, considering "*" along with previous column values /marks and for "FFF" trying to consider them along with next / same column. Applied logic that if there is such a string then GrdPnt & Crd Pnt will be 0 ( Zero).
22nd December 2023
| 22nd December 2023 - Phone call discussion with Tejaswini Ma'am- | She said do not consider 2019. 2022, - 2023 |  | Getting all marks corresponding to there distributions. However did transformation for this. And did this based on First semesters data. | Getting all marks corresponding to there distributions.
23rd December 2023
|  |  |  | 1) Extarcted Sem1 records as per the October 2019 pattern. Howevere it is not complete pattern. i.e. Int, Ext... grades distribution. 2) Today I started working on 2022 & 2023 ledgers. i.e. April 2022, October-2022 & April-2023. 3) Extarcted first student's basic info. Facing so many difficulties & almost working from start again..... | YearWise_StudentInfo_df PRN, Seat No, Mother Name, Student Name, Student Info, Ledger Year, Course Pattern Year
24th - 27th December 2023
|  |  | Got Grades & SGPA & YearWise Result for - 1) October 2022 2) April 2022 3) April 2023 4) October 2021 ... All follows same makrs distribution i.e. 18 grades/columns | 1) Extracted grades for 3 ledgers however not getting PRN, Seat No, & Mother Name in that df. 2) SGPA for each semester is remaining. | I was facing difficulties to get right grades into that particular column now, performed transformations and got the grades correctly in relevant columns.
28th December 2023
1) We need to follow different logic to extract following ledgers, ---- October 2019, ---- October 2020 As these are following same gade distribution i.e. 16 columns for marks
Findings:- 1) Subject codes are differnt than what was given by BNCA Team, i.e. ther are characters at the end of subject codes. Not all but 'Audit Course' has - 2201935F, 1201918A, etc. 2) Found 2 new subjects and there subject codes:- Subject codes- 9201917 AND 22999 Subject Name- Physical Education AND Democracy Election and Governance.
|  |  |  | 3) Ledgers are not same.- A] Below ledgers have same marks distribution i.e. 18 columns are there for marks. 1) April 2022, 2) April 2023, 3) October 2021- For a few students we don't have Year Result records. 4) October 2022. B] Below ledgers have same marks distribution i.e. 16 columns are there for marks. 1) October 2019 - Here in this ledger we have First Semester data only. 2) October 2020 4) While getting YearWise_Result there are a few records who have - " First Year Total Credits Earned 56/56 " And a few ledgers have - " FourthYear Result: Fail A.T.K.T. " " Total Credits Earned: 49/56 " | Note: Last time we had found C.G.P.A. / Classes like First Class With Distinction / Higher Second Class / Second Class / Fail / Fail with A.T.K.T. However current/latest ledgers don't have other than Fail, Fail With A.T.K.T. OR Anything else.
29th December 2023
|  |  |  | 1) There are two ledgers of October 2022. So to avoid overlapping of records we need to use different logic to segrigate these ledgers. | To do so adding new column into Student Info Dataframe. i.e. Root dataframe. Column Name is "Ledger Release Date" this will help us to identify each ledger seperately.
Extracted ledger dates but now facing new issues of partition, not getting two page records. Getting correct partitions as per the previous code but after integrating the new modification i.e. 'Ledger Release Year' code got isturbed need to update the code for first root df. Because of partition issue not getting all semester's SGPAs and Results as well.
3rd January 2024
|  |  |  | 1) Added two more columns into YearWise_Grades_df:- -----Grades Semester Name, -----Grades Year Name. 2) Interns require semester Names and Year Names seperately and Semester name should be character only. | As per interns requirement dataframe is created and shared the code on 4th January 2024
7th January 2024
1) Fetching two page records of all the five ledgers along with release dates.
2) Pattern 16 -?
3) For one ledger we need to either keep the separate code or integrate seperate conditions
4) Checking other patterns on the same code.
9th January 2024
April-2020, April -2019, & October 2019 - All are of Pattern 16. ---Need to work on these ledgers as well
1) April-2021 ---> Grades are shifted to next line. 2) October 2019 Grades are 18
10th January 2024
Subject codes for 2015 Ledgers are differnt so need list of the same.
Let's work one by one- April -2021 1) Grades are 18 however crd pnt shifted on next line. Facing issue while extracting the records for above ledger using existing code.
|  |  | Extracted the dates for October 2019 and April 2020 | 2) Not able to fetch release date for October 2019 & April 2020
3) Trying to get Both grades 16 & 18 using one code To do so - while performing the transformation shiftting the columns for October -2019 and April - 2020 grades
11th January 2024
|  |  | Got Combine 16 & 18 column grades using same grade extraction code. SGPA & Result also extracted. | 1) Got Combine 16 & 18 column grades using same grade extraction code. Added shift_grade() function before transformation. 2) SGPA & Result also extracted However next line grade & C.G.P.A. is still not able to extract.
|  |  | Now got all ledgers dates using one function -Dates are: ---- 21-Jul-2020 ---- 25/Jan/2020 ---- 28-Aug-2021 | April 2021 & April 2020 release dates are on same line where Savitribai Phule is written. - This causing problem.
3) April- 2020 ---- Have C.G.P.A. & October-2019 ------ Common thing in both is the gardes are 16.
24th 12th January 2024
TO-DOs
1) April-2021 ----> Next line grade extraction
|  |  | C.G.P.A. & Class are extracted. | 2) April-2020 -----> C.G.P..A. extraction
3) Credit criteria based result.
25th January 2024
1) Working on 2015's Pattern as well. Using PRN Code. Facing issues need to shift grades.
2) Facing issues while getting next line grades & Seperation of Subject code and Subject Name needs to be done, as its not extracting that line. i.e. thare are a records where we are getting Subject codes and theris name together without space.---April- 2021 Ledger
|  |  | Had meeting with SSPU team they said we are working on to fix structure of all these ledgers and it will be implemented in October 2024 Ledgers. | After working on these ledgers, issues which we are facing right now i think we need to fixed the ledger structure otherwise it is very difficult to get all the extraction work done, that also using same code. | So fixing meeting with SSPU on 29th / 30th January 2024
3rd February 2024
Received 10 new college ledgers of Pattern 2015 - Seems the structure is again not same.
10th February 2024
1) Pattern 19 and 2015 common extraction.
|  |  | Subject names and code are getting now for 2015 | 2) Subject Code insertion for pattern 2015.
|  |  |  | 3) Both Grade pattern extraction, i.e. 16 and 18 grades of bothe year patterns 2019 and 2015 | Need to perform transformation for 2015 pattern differently because grades are 16 here.
4) Next line grade issue - Shifting the grade back to its grade line.
5) Seperation of Subject Name and Subject Code from the grade lines of April 2021.
6) Exampted records - insertion of the same.
7) Missing marks or records data. -How to replace / extract, in what format.?
12th February 2024
1) Found new variations in 2015 ledgers. --- There are a few subject codes which are together i.e. two subject codes are combined. A) 1201502 & 3. B) 1201510 & 11 C) 2201518 & 19 D) 2201521 & 22 E) 2201527 & 28 F) 2201530 & 31
2) Extra subject added - 9201517
13th February 2024
1) Grades are 4 digit for example, *018, *042 or P017, P032
Work done till 13th February 2024
Extracted 10 files of pattern 15's 2 files and remaining 8 are of pattern 19. However both patterns have different grades distribution 16 & 18. so extracted that as well.
Basically from root df to screen1 and screen2 df everything is fine. Testing is needs to be done
Next line grade issue is still not resolved working on that only.
Exampted rocords are also not coming in proper format.
15th February 2024
|  |  | Resolve this issue but code got disturbed again. | Trying to get + sign however code is getting distrurb
Resolve this issue but code got disturbed again. Grd Pnt.
Not geting GrdPnt correctly because all the credits off A+ Grade got shiftted to right side.
Need to Write a separate transformation for either 2015 pattern records or records having '+' sign in grade.
17th February 2024
Logic 1: If the grade line contains + sign then consider the Tot as grade -> then Tot_FF as Grd Pnt & crd as Crd Pnt.
Logic 2: Change grade extraction code itself.
13th March 2024
1) Will work seperately on different patterns i.e. 2019 and 2015
2) Current issues are - I) Next line shifted grade extraction. ii) Exampted record extraction, iii) + Sign extration from patten 2015, iv) different grades for different patterns. - Grade 18 and 16 we need to extract together in one go.
19th March 2024
Ledgerwise findingds and issues-
Apr-2021 -1) Exampted records are there, 2) Grades are shifted to nect line, 3) Subject names and codes are coming together, which is why not getting such line records.
20th March 2024
|  |  |  | Wanted to check each 2019 ledger records so tried testing on Oct-2019 after mergin the C.G.P.A. and Grades df not getting Year Oct-2019 records...nedd to figure out this.... | Check join while merging
Pat19_YearDateWise_Grad16_18_Info_df1923 and P19_YearDateWise_SGPA_YearResult_CGPA_Info_df1923 We have Ledger Year = Oct-2019 However after merging these two dfs we are not getting any records for Oct-2019
Same testing is done for Apr